## Product Backlog
BrightPath IELTS — Product Backlog (4 Sprints)
ID | Type | Sprint | Priority | Title | Description / Note | Status
TECH-01 | Task | 1 | Critical | Project Repo & Toolchain Setup | Init Git repo, SCSS build pipeline, folder structure for all pages. | Done
US-1.1 | Story | 1 | High | Homepage UI | Static homepage: hero, featured courses carousel, teacher highlights, navbar. | Done | Sprint 1 — UI/Static Frontend
US-1.2 | Story | 1 | High | Category / Course Listing Page | Course card grid with filter UI (band score, skill). Static data. | Done | Sprint 2 — Auth & User Management
US-1.3 | Story | 1 | High | Course Detail Page | Full detail: description, syllabus accordion, teacher snippet, enrol CTA. | Done | Sprint 3 — Core Features & Payment
US-1.4 | Story | 1 | High | Teacher Profile Page | Bio, IELTS score badge, experience, linked courses. | Done | Sprint 4 — Advanced Features & Admin
US-1.5 | Story | 1 | Medium | Shopping Cart Page | Cart with line items, remove option, subtotal. | Done
US-1.6 | Story | 1 | Medium | Checkout & Order Confirmation Pages | Checkout form layout + order-completed confirmation screen. | Done
US-1.7 | Story | 1 | Medium | Sign-In & Sign-Up Pages (UI only) | Auth forms with HTML5 validation; no backend wiring. | Done
US-1.8 | Story | 1 | Low | Student Profile Page (UI only) | Profile layout: avatar, enrolled courses, edit form placeholders. | Done
TECH-02 | Task | 2 | Critical | Database Schema Design | ERD: Users (Student/Teacher/Admin), Courses, Enrolments, Payments. Setup PostgreSQL. | To Do
TECH-03 | Task | 2 | Critical | Backend API Scaffold | REST API skeleton, ORM, auth middleware, environment config. | To Do
US-2.1 | Story | 2 | Critical | Student Registration | POST /auth/register — validate email, hash password, create session. | To Do
US-2.2 | Story | 2 | Critical | Student Login | POST /auth/login — verify credentials, issue JWT, role-based redirect. | To Do
US-2.3 | Story | 2 | High | Logout | Invalidate session; protect all authenticated routes. | To Do
US-2.4 | Story | 2 | Critical | Teacher Login | Same login endpoint; role detection → teacher dashboard. | To Do
US-2.5 | Story | 2 | High | Admin User Management Panel | Admin UI + CRUD API: list, activate/deactivate/delete users, search. | To Do
US-2.6 | Story | 2 | High | Student Profile Management | GET/PUT /users/:id — edit name, password, avatar. | To Do
US-2.7 | Story | 2 | Medium | Password Recovery via Email | Forgot-password email with 24h reset link. | To Do
TECH-04 | Task | 3 | High | Payment Gateway Integration | Integrate VNPay/MoMo SDK + webhook callback handler. | To Do
TECH-05 | Task | 3 | High | File Storage Setup | S3-compatible bucket for videos/docs; pre-signed URLs. | To Do
US-3.1 | Story | 3 | Critical | Course Purchase & Enrolment | POST /orders → payment gateway → callback → grant enrolment. | To Do
US-3.2 | Story | 3 | High | Online Course Player | HLS video player, downloadable materials, resume progress tracking. | To Do
US-3.3 | Story | 3 | High | Mock Test / Exercise Module | Test engine: timed questions, answer submission, score + results. | To Do
US-3.4 | Story | 3 | High | Offline Class Registration | Slot counter; POST /enrollments/offline; full-class guard. | To Do
US-3.5 | Story | 3 | High | Teacher — Upload Course Content | Multipart upload to S3, attach to course section, reorder. | To Do
US-3.6 | Story | 3 | Medium | Teacher — Student Progress View | List enrolees with % progress and last-active timestamp. | To Do
TECH-06 | Task | 4 | Medium | Recommendation Engine | Rule-based: suggest courses by band score gap and skill; exclude enrolled. | To Do
US-4.1 | Story | 4 | High | Personalised Course Recommendations | Recommended for You section powered by recommendation engine. | To Do
US-4.2 | Story | 4 | Medium | Related Courses & Suggested Teachers | Course page: Related Courses + Suggested Teachers sections. | To Do
US-4.3 | Story | 4 | High | Student Learning Progress Dashboard | My Learning: % per course, overall badge at 100%. | To Do
US-4.4 | Story | 4 | High | Admin Course Management | Admin CRUD for courses: create, edit, publish, archive. | To Do
US-4.5 | Story | 4 | Medium | Admin Sales & Enrolment Reports | Revenue by course, enrolments over time, date-range filter. | To Do
TECH-07 | Task | 4 | Low | Performance & SEO Optimisation | Lazy-load images, paginate APIs, meta tags, Lighthouse ≥ 80. | To Do